## Summary
Status after the 12 Oct session | Master Test Plan items | New items from this session | Total
Confirmed | 4 | 13 | 17
Partially confirmed | 6 | 1 | 7
Still open | 9 | 0 | 9
Closed | 1 | 0 | 1
Total | 20 | 14 | 34

## About This Workbook
Field | Value
Purpose | One view of every Sprint 1 clarification and TBD: what was answered on 12 Oct 2026, what remains to be determined.
Primary sources | 1) Sprint 1 Requirement Refinement Meeting recording, 12 Oct 2026, 30 min 13 s. 2) MoE_Agile.md pre-meeting Q&A. 3) Master Test Plan v1.0-r1 ASM/TBD register. 4) MoE_MasterFile.md backlog and ACs for cross-checks.
Status legend | Confirmed = customer/trainer answer available; Partially confirmed = direction agreed, specific values or policies still open; Still open = not addressed yet, never assume; Closed = no action needed.
ID rules | ASM-xx and TBD-xx are stable IDs from the Master Test Plan — never renumber. NEW-xx are new items captured from this session; propose folding them into the Master Test Plan register (TBD-18+) at the next revision (v1.1).
Sheet index | Summary (counts) · TBD Register (every item and status) · Clarification Log Updates (Sprint 1 log items affected) · Meeting Q&A (full Q&A from the recording) · MoE Agile File Q&A (pre-meeting answers).
Caveat | Where the recording wording is unclear, this register follows the confirmed intent; anything not explicitly confirmed stays OPEN.
Companion document | `output/MOE_Sprint1_Requirement_Refinement_Summary.md` + `.docx` (readable English summary for the team).

## TBD Register
ID | Category | Item | Status in MTP (before) | Status after 12 Oct session | Clarified / current position | Still open / next step | Source | Owner | Related requirement
ASM-01 | Sprint scope | Sprint 1 scope (proposed): R1-R3 + R8 core happy path, R10 family-application draft as a stretch item, architecture / integration contract. | To be determined | Still open | Not covered in the 12 Oct session. | Lock the Sprint 1 committed scope at the Day 1 Requirement Lock. | Master Test Plan v1.0-r1 | PO / BA | R1-R3, R8, R10
ASM-02 | Roles | Student is not a portal user; parents manage accounts and pay on behalf of children. | Open | Confirmed | "Students are too young for a SingPass account, so they have no role and cannot access the system. Parents use the child's education-account balance to pay." (Same answer in MoE_Agile.md.) | None. | Meeting 12 Oct | BA | R8-R10
ASM-03 | AI scope | AI features are bonus scope, excluded from mandatory release gates. | Open | Still open | Customer encourages AI (for example an SBFAS recommendation) but AI stays optional; Go/No-Go decision in Sprint 3. | Confirm AI scope at the Sprint 3 Go/No-Go; boundaries still in TBD-13. | MoE_MasterFile.md / project summary | PO | R4 (AI), R8 (AI)
TBD-01 | Account age boundary | 29 Feb births: age triggers are evaluated as of 1 Mar 00:00 in non-leap years. | Confirmed | Confirmed | Not re-discussed; keep the confirmed rule in test data. | None. | Master Test Plan (prior) | BA | R1
TBD-02 | Account lifecycle | Account status when a student drops out before age 16. | Open | Still open | Not covered in the 12 Oct session. | Confirm before lifecycle state tests. | - | BA | R1
TBD-03 | Account lifecycle | Creation timing when a child becomes a Singapore Citizen after age 7 (immediate or batch). | Open | Partially confirmed | Mechanism confirmed: citizenship data arrives from a trusted MHA feed (files maybe weekly or daily, configurable) including delta changes such as new citizens, so creation is driven by feed processing. | Define the mock feed contract (fields, frequency) for Sprint 1. | Meeting 12 Oct | BA / DEV | R1
TBD-04 | Account lifecycle | Citizenship lost before age 16: account handling and remaining balance. | Open | Still open | The feed must deliver citizenship-conversion delta changes, but what happens to the account or balance is still unconfirmed (working rule: flag for MOE HQ review, no automatic close). | Confirm account and balance handling, including any re-acquisition path. | Meeting 12 Oct (partial) | BA | R1
TBD-05 | Account closure | Destination account for the closing balance; failed-transfer handling. | Open | Confirmed | Destination = CPF. A mock API may be used — real CPF integration is not required. | Failed transfers keep the working rule: flag for manual MOE HQ handling (AC-018-02). | Meeting 12 Oct | BA | R1
TBD-06 | Payment | Supported payment methods and refund policy; split payment deferred. | Open | Partially confirmed | Methods confirmed: credit card, PayNow (Singapore QR) and NETS. | Refund policy still open; split/combined payment still deferred pending confirmation. | Meeting 12 Oct | BA | R9
TBD-07 | FAS | MOEFAS / SBFAS exclusivity and precedence. | Open (assumption-based) | Partially confirmed | "They cannot enjoy both." Assessment runs on MOEFAS first; only if not eligible does the school assess SBFAS. MOEFAS normally provides more support. School SBFAS allocation for non-MOEFAS students is the requirement. | Multi-tier selection within one scheme ("higher subsidy applies") remains a working assumption. | Meeting 12 Oct | BA | R4
TBD-08 | FAS | One active FAS application per child per period; family applies once for all children. | Open (assumption-based) | Still open | Not covered (R10 was not discussed). | Confirm before R10 test design (Sprint 2). | - | BA | R4, R10
TBD-09 | Hardcopy FAS | Field entry, validation and assessment defined; open points: scan file type and size; OCR not required. | Open (narrowed) | Still open | Not covered. | Set the allowed scan file type and size limit. | - | BA | R5
TBD-10 | Simulation | Simulation is read-only; sessions are logged. | Closed | Closed | No change. | None. | Master Test Plan (prior) | BA | R7
TBD-11 | Budget | Warning thresholds (80% / 100%), no blocking; budget period basis. | Open (assumption-based) | Partially confirmed | Budget model reframed: one overall yearly (lump-sum) budget per fund; no per-person cap — the school decides how many students receive grants and how much each receives. | Warning thresholds and the budget period basis (assumed academic year) are not yet explicitly confirmed. | Meeting 12 Oct | BA | R6
TBD-12 | Roles / permissions | Exact permission matrix between MOE HQ and School users. | Open | Still open | Team direction (MoE_Agile.md): one system with role-based access; the team will define the matrix itself instead of asking the customer. | Publish the role-versus-function matrix before permission test design (Day 1). | Meeting / MoE_Agile.md | BA + DEV | R1, R3, R4, R6, R7
TBD-13 | AI | AI integration boundaries: model input/output, confidence, fallback, error handling. | Open | Still open | Not covered; AI remains optional. | Define only if the Sprint 3 AI Go decision approves it. | - | PO | R4 (AI), R8 (AI)
TBD-14 | Environment | Test environment specifics and external sandbox availability. | Open | Partially confirmed | Mock integrations are acceptable: CPF transfer (mock API), income service ("treat as a mock file"); a SingPass mock is already planned for Sprint 1. | Hosting, database, accounts and sandbox details still to be defined; gates SIT scheduling. | Meeting 12 Oct | QA / System Owner | R1-R10 (all)
TBD-15 | Account creation | Opening balance of a newly auto-created account. | Open | Confirmed | "Initial balance is always zero." Standard practice: a top-up is scheduled for newly opened accounts right after opening. | None. | Meeting 12 Oct | BA | R1
TBD-16 | Top-up | Maximum single top-up amount and validation limit. | Open | Partially confirmed | Configurable upper-limit concept confirmed (an account can only hold up to a maximum). | The numeric maximum is still to be set. | Meeting 12 Oct | BA | R2
TBD-17 | Hardcopy FAS | Allowed attachment file type and size. | Open | Still open | Not covered. | Set the limit before upload boundary tests. | - | BA | R5
NEW-01 | Account closure | Unpaid fees on closure day: does the balance settle them, and is closure blocked? | Not tracked (new) | Partially confirmed | Closure is NOT blocked by unpaid fees; outstanding amounts are chased from parents separately (bad debt). | Whether the remaining balance settles outstanding fees BEFORE the CPF transfer is not confirmed. | Meeting 12 Oct | BA | R1, R9
NEW-02 | Data integration | Trusted citizenship feed from the Ministry of Home Affairs (MHA) for Singapore Citizens aged 7-16. | Not tracked (new) | Confirmed | Trusted source; full file plus delta changes (new citizens, citizenship conversions); file frequency configurable (weekly or daily); the system decides how to process the file (consider processing time). | Mock feed contract (fields, frequency) needed for Sprint 1 development and tests. | Meeting 12 Oct | BA / DEV | R1
NEW-03 | Account / nationality | Dual-citizenship students. | Not tracked (new) | Confirmed | Treat dual-citizenship cases as Singaporean; they cannot receive two subsidies. Terminology: "scholarship" is not a "subsidy" — keep the words correct. | None. | Meeting 12 Oct | BA | R1, R4
NEW-04 | Account scope | Singapore Citizen studying overseas / international school at age 7. | Not tracked (new) | Confirmed | The account is still created and activated at age 7; offline claiming through MOE exists but is out of scope for this project. | None (scope exclusion recorded). | Meeting 12 Oct | BA | R1
NEW-05 | Funding scope | Which funds the project models. | Not tracked (new) | Confirmed | Only two funds: the education-account fund and the MOE FAS fund. Ignore other real-world funds (ComCare, Straits Times School Pocket Money Fund, bursaries, etc.). | None. | Meeting 12 Oct | BA | R2, R4
NEW-06 | Fee scope | Which fees the system handles. | Not tracked (new) | Confirmed | Only fees generated inside the system; external fees (for example taxes) are not considered. | None. | Meeting 12 Oct | BA | R3, R9
NEW-07 | Top-up | Approval step for top-ups (single vs batch). | Not tracked (new) | Confirmed | No approval process required now (HQ users set up the rules). An approval step is a plus point if built — ideally configurable on/off. | Treat as an optional enhancement, not a release gate. | Meeting 12 Oct | PO / BA | R2
NEW-08 | Fees | Which fee components the education account can pay. | Not tracked (new) | Confirmed | Make it configurable — policy may change (today all components may be payable; future scope may differ). | None. | Meeting 12 Oct | BA | R3
NEW-09 | FAS | FAS eligibility configuration. | Not tracked (new) | Confirmed | Eligibility must be configurable, not hard-coded: household income band, per-capita income band and citizenship. Do not hard-code researched policy. | None. | Meeting 12 Oct | BA | R4
NEW-10 | Data integration | Income service query behaviour. | Not tracked (new) | Confirmed | Query by NRIC returns: number of family members in the household; total household monthly income range; per-capita income range. Never exact amounts. A mock file is acceptable for this project. | None. | Meeting 12 Oct | BA / DEV | R4
NEW-11 | School data | Who creates school records. | Not tracked (new) | Confirmed | Schools are created manually by MOE HQ users. | Later detail (edit/delete rules) stays with SCH-01 / SCH-04 in the clarification log. | Meeting 12 Oct | BA | R3
NEW-12 | School data | Levels / classes / cohort structure. | Not tracked (new) | Confirmed | Levels contain different classes (class names vary, including descriptive names); students belong to classes; students may move school when they move house; "cohort" refers to levels (not admission year). | Field-level model still needed (SCH-03 in the clarification log). | Meeting 12 Oct | BA | R3
NEW-13 | FAS process | School user process to allocate SBFAS money. | Not tracked (new) | Confirmed | Manual process: receive applications, review them (for example a family with five children may be needier), select students in their school, and assign a subsidy amount. An AI recommendation is an optional bonus. | None. | Meeting 12 Oct | BA | R4, R6
NEW-14 | Top-up | Top-up rule model: fixed amount vs account balance. | Not tracked (new) | Confirmed | Support both: fixed-amount top-ups and balance-based conditions with a configurable upper limit; top-up rules are configurable. | Numeric limits still open (TBD-16). | Meeting 12 Oct | BA | R2

## Clarification Log Updates
Log ID | Update from this session | Action
SCH-03 | "Cohort" refers to levels (confirmed) — not the intake year. | Correct the working assumption before test design; Level / Cohort / Class field lists are still needed.
SCH-01 | Schools are created manually by HQ users. | Partial answer to "who creates schools?"; the school field specification is still needed.
ACC-01 | Creation is citizenship/age-driven through the trusted MHA feed; school enrolment is not required (overseas students still activate at age 7). | Update the question; the exception list is still to be confirmed.
ACC-02 | Opening balance is always zero; a top-up can be scheduled right after account opening. | Answered — update the log.
ACC-06 | The closing balance transfers to CPF; a mock API is acceptable. | Answered — update the log; the transfer story stays in Sprint 2 (US-016).
ACC-10 | Creation/closure processing follows the MHA feed (weekly or daily, configurable). | Still need the QA manual trigger and job schedule details for the test environment.
TOP-01 | Top-up model: fixed amount and/or balance-based with a configurable upper limit; rules configurable. | Update the question; numeric min/max values still to be confirmed (TBD-16).
TOP-04 | Balance conditions are confirmed in scope ("we care about the account balance as well"). | Criteria list and operators still to be defined.
GEN-05 | Direction: one system with role-based access; the team will define the permission matrix (not ask the customer). | Publish the role-versus-function matrix before test design.

## Meeting Q&A (12 Oct)
# | Topic | Question | Confirmed answer | Related register item | Note / follow-up for the team
1 | Roles | What is the main purpose of each role in the system? | MOE HQ: manage everything related to the finance system. School users: their purpose is already described in the user stories. | - | Lesson: do not ask questions the user stories already answer.
2 | Funding | Where do MOE HQ top-up funds come from? | From the government budget — a dedicated education-account fund supplies the top-ups. | NEW-05 | -
3 | Funding | Can the account also receive other funds (ComCare, Straits Times School Pocket Money Fund, bursaries...)? | Ignore those for this project: model one fund for the education account and one fund for MOE FAS. | NEW-05 | Do not build other funds.
4 | School data | How are levels, courses and classes structured? | Levels contain different classes; class names vary (may be descriptive, not only numbers/letters); students belong to classes; students may move school if they move house. | NEW-12 | Keep class naming flexible.
5 | School data | Does "cohort" mean the same academic level/year, or the same admission year? | "Cohort refers to levels." | NEW-12 | Fix any intake-year assumption in the backlog/ACs.
6 | Fees | Can the education account pay every fee component, or only some? | Make it configurable — policy may change over time. | NEW-08 | Configuration, not hard-coding.
7 | Roles | In R3, how do students use the account? Do students have a role? | No student role — students are too young for SingPass and cannot access the system; parents pay using the child's account balance. | ASM-02 | -
8 | Top-up | Does a batch top-up need second-person approval? | No approval needed for now; an approval step is a plus point if built, best made configurable (on/off). | NEW-07 | Optional enhancement only.
9 | Account data | Which data source verifies student information before auto-creating the account at age 7 (MyInfo / SingPass)? | A trusted source — the Ministry of Home Affairs sends Singapore Citizen data (ages 7-16) as files (maybe weekly or daily; configurable). Plan for delta changes: new citizens and citizenship conversions. | NEW-02, TBD-03, TBD-04 | Need a mock feed contract for Sprint 1.
10 | Nationality | Dual citizenship: prioritize Singapore? Two subsidies? | Treat dual-citizenship cases as Singaporean. No double subsidies. Use the words correctly: a scholarship is not a subsidy. | NEW-03 | Terminology discipline.
11 | Account | Citizen turning 7 while studying overseas — still activate the account? | Yes, still activated at age 7. Offline claiming through MOE exists but is out of scope for this project. | NEW-04 | Scope exclusion.
12 | Account closure | Where is the remaining balance transferred when the account closes? | To CPF. A mock API can be used — the real integration is not required. | TBD-05 | -
13 | Top-up | Is the MOE top-up based on the account balance, or a fixed amount? | Support both: fixed-amount top-ups and a configurable upper limit (the account can hold at most a set amount). Rules must be configurable. | NEW-14, TBD-16 | Numeric limit still open.
14 | Account closure | On closure day with unpaid fees: settle them first? Does closure get blocked? | Unpaid fees do NOT block closure; outstanding amounts are chased from parents separately (bad debt). | NEW-01 | Whether the balance settles fees before the CPF transfer is NOT confirmed.
15 | Account creation | Does a new account get an initial amount? | Initial balance is always zero; a top-up is normally scheduled right after opening. | TBD-15 | Zero expected in test data.
16 | Payment | Which payment methods are provided in the system? | Credit card (common cards), PayNow (Singapore QR) and NETS. | TBD-06 | Refund policy still open.
17 | FAS | If eligible for both MOEFAS and SBFAS, which one applies? | They cannot enjoy both. Assess MOEFAS first; only if not eligible does the school assess SBFAS. MOEFAS normally gives more. | TBD-07 | -
18 | FAS | Can school users allocate SBFAS to students without MOEFAS? | Yes — that is the requirement. | TBD-07, NEW-13 | -
19 | Fees | Do we handle only system-generated fees, or external fees too? | Only fees generated in the system. | NEW-06 | -
20 | Budget | What happens when the SBFAS/MOEFAS budget reaches the 100% cap? | The budget is one overall yearly lump sum; there is no per-person cap — it does not matter how many students receive grants or how much each receives. | TBD-11 | Warning thresholds still to confirm.
21 | FAS process | What is the school user's process to allocate money to students? | Manual: review incoming applications, select students of their school, assign a subsidy amount; AI can recommend later (bonus). | NEW-13 | Manual in scope; AI optional.
22 | Data | Where does family information (income, members) come from? | A third-party system returns ranges only, never exact amounts. Mock file: query by NRIC returns household member count, household monthly income range and per-capita income range. | NEW-10 | Mock accepted.
23 | School data | Can MOE create schools? | Schools can be created manually by HQ users. | NEW-11 | -
24 | Process | Meeting etiquette. | Ask the client's permission BEFORE recording any meeting or session. | - | Apply to all future sessions.
25 | Process | Question quality. | Keep questions specific and consolidated; do not ask what the user stories already answer. | - | One 30-minute slot per sprint.

## MoE Agile File Q&A
# | Topic | Question | Answer / decision in MoE_Agile.md | Status | Related register item
1 | Architecture | Two systems — same gateway or separate? | Team decision: one system with role-based access (no customer question needed). | Team decision | TBD-12
2 | Roles | What is the main purpose of each role? | MOE HQ: manage every finance-related matter. | Answered | -
3 | Funding | Money sources to integrate (Edusave, ComCare, STSPMF, bursary...)? | Ignore all others — only the MOE education-account fund and the FAS fund. | Answered (also confirmed in the meeting) | NEW-05
4 | Student role | R3: do students use the account / POSB Smart Buddy integration? | No student role; the parent uses the student's education-account balance. Team note: the parent is expected to view fees payable, register bank-account details and view payment history. | Answered | ASM-02
5 | Admin modules | Review of the proposed module structure / missing functions / role restrictions? | Team decision: DEV defines the module structure and raises questions as they arise; permissions are defined by the team. | Team decision | TBD-12
6 | School structure | Levels / Cohorts / Classes structure; cohort meaning. | Levels to different classes (varied names) to students. Cohort meaning was asked in the meeting: "cohort refers to levels". | Answered in meeting | NEW-12
7 | Fees | Can the education account pay every fee component? | Asked in the meeting: make it configurable. | Answered in meeting | NEW-08
8 | Top-up | Who gets a top-up? By age/enrolment/balance? Limits? | Team decision: admins configure top-up rules themselves. Meeting confirmed the model: fixed amount and/or balance-based with a configurable upper limit. | Team decision + meeting confirmation | NEW-14, TBD-16
9 | Top-up approval | Single top-up automatic, batch needs approval? Threshold? | Asked in the meeting: no approval required now; optional configurable approval is a bonus. | Answered in meeting | NEW-07
10 | Unpaid fees | Which unpaid fees count as outstanding? Pay the oldest first? | Team decision (not customer-confirmed): the system will apply the oldest fee first, oldest to newest. | Team decision | Payment design (R9)
11 | Account data | Data source before activating an account at age 7 (MyInfo / SingPass)? | "Treat it as a trusted source of data" — the meeting confirmed the MHA citizenship feed. | Answered | NEW-02, TBD-03
12 | Account lifecycle | If a student dies or loses citizenship — deactivate? Reactivate if citizenship returns? | Marked as not-to-ask at kick-off; no answer recorded — remains open. | Open | TBD-04
13 | Nationality | Dual citizenship: prioritize Singapore? Two subsidies? | Treat as Singaporean; no two subsidies. | Answered (also in the meeting) | NEW-03
14 | Account | Overseas school at age 7 — still activate? | Still activated at 7; the offline claim path is out of scope. | Answered (also in the meeting) | NEW-04
15 | Balance | Closed account: where does the balance go? | CPF. | Answered (also in the meeting) | TBD-05
16 | Closing day | Pending payments on the closing day; who fixes a failed CPF transfer? | No answer recorded — remains open (the meeting only covered unpaid fees at closure). | Open | NEW-01, TBD-05
17 | Budget | What happens at the 100% budget cap? | Unanswered in the file; the meeting gave the model: one overall yearly budget, no per-person cap. | Answered in meeting | TBD-11
18 | Payment scenarios (research) | Edusave + GIRO shortfall examples (three cases: fund covers the bill, fund covers part, fund empty). | Team research notes about how real schemes work — NOT customer-confirmed. Keep as context only; do not turn into requirements. | Internal note | Payment design (R9)