## Sprint Backlog 1
| PBI Ref | Task ID | Category | Task Title | Description | Assignee | Estimate (Hours) | Priority | Status | Definition of Done (DoD)
R1 | PB-05 | TSK-R1-01 | Documentation | Draft Technical Specification Docx for R1 (Education Account Lifecycle) | Write detailed .docx specification covering business flows for account creation/activation at age 7 and closing/transfer to CPF at age 16; design account state machine, cron triggers, API specs, and edge cases (citizenship change, leap year birthdays). | Kevin,Hugh | 4 | P1 - High | Done | Complete .docx file adhering to team standards; includes full Sequence Diagram, State Transition Diagram; reviewed & signed off by BA and Lead.
R1 | PB-05 | TSK-R1-02 | Database Refinement | Design Data Model & Migrations for Education Account Lifecycle | Design data model and database schema for Education Account lifecycle, balance tracking, and status transitions based on technical specification; create migration scripts with rollback support. | Hugh | 5 | P1 - High | Done | Database schema reflects technical specification; ERD and Data Dictionary fully updated; migration and rollback scripts tested successfully without errors.
R1 | PB-05 | TSK-R1-03 | Backend Core | Build Scheduled Job to automatically create & activate accounts at age 7 | Implement scheduled background job periodically scanning eligible Singapore citizen students turning 7 based on date of birth; initialize Education Account records with active status and zero balance according to business rules. | Kevin | 4 | P2 - Medium | Done | Processing logic accurate by date of birth; idempotent execution (no duplicates on re-run); Unit Test coverage >= 85%; test cases for edge conditions (non-citizen, under 7 years old).
R1 | PB-16 | TSK-R1-04 | Backend Core | Build Scheduled Job to automatically close accounts & transfer settlement to CPF at age 16 | Implement scheduled job checking accounts turning 16: verify no pending transactions or unsettled debts, transition status to closed, and log settlement transfer to CPF system. | Kevin | 4 | P1 - High | Done | Account transitions to closed status, redundant balance sent to CPF; comprehensive audit logging; new transactions blocked on closed accounts
R1 | PB-05 | TSK-R1-05 | Backend / API | Build Wallet CRUD APIs (create, credit, debit, update status, and get wallet) & Wallet Transaction functionality to handle wallet behavior, including APIs to retrieve and reverse transactions. | Implement Wallet APIs to manage wallet lifecycle and balance operations, including creating wallets, crediting and debiting balances, updating wallet status, and retrieving wallet information. Implement Wallet Transaction functionality to handle wallet-related transactions, ensure proper transaction processing, and provide APIs to retrieve transaction history and reverse transactions when needed. | Hugh | 8 | P1 - High | Done | Transactions using the education account must follow business rules; valid Singapore citizen accounts verified; balance deducted accurately with atomic rollback on failure; full transaction logging; Unit Test coverage >= 85%.
R3 | PB-02 | TSK-R3-01 | Documentation | Draft Technical Specification Docx for R3 (Master Data & Fee Management) | Write detailed .docx specification covering school hierarchy (School, Level/Cohort, Class, Student), RBAC permissions matrix (MOE HQ vs School User), and fee structure/components (tuition, miscellaneous fees, optional GST). | Nito, Tyson | 6 | P1 - High | Done | Complete .docx document adhering to team standards; includes ER diagrams, role permission matrix, and fee calculation flow; reviewed and approved by PO and Dev Lead.
R3 | PB-02 | TSK-R3-02 | Database Refinement | Design Data Model & Migrations for School Master Data & Fee Catalog | Design data model and database schema for school organization master data and fee catalog based on technical specification; establish composite indexing, constraints, and migration scripts with rollback. | Nito, Tyson | 7 | P1 - High | Done | Database schema verified against master data and fee requirements; ERD and Data Dictionary finalized; migration and rollback scripts execute smoothly.
R3 | PB-02 | TSK-R3-03 | Backend Core | Build Master Data CRUD APIs (School, Level, Class, Student) and RBAC Guard | Develop master data management APIs for schools, levels, classes, and students; integrate RBAC guard ensuring MOE HQ has broad management access while School users are restricted to their permitted school scope. | Nito, Tyson | 8 | P1 - High | Done | 100% pass on cross-authorization security tests (School User cannot modify other schools); strict API validation via DTO; code review achieves 2 approvals.
R3 | PB-12 | TSK-R3-04 | Backend Core | Build Fee Type Configuration Module & Student Charge Generation | Build backend service allowing configuration of fee types with reusable fee components, and generate payable student charges per cohort/class according to business rules. | Nito, Tyson | 8 | P1 - High | Done | Total calculation and fee component breakdown logic strictly accurate without rounding discrepancies; supports batch charge insertion; Unit Test coverage >= 85%.
R3 | PB-03 | TSK-R3-05 | Frontend / UI | Build School Management & Fee Configuration UI (Admin Portal) | Build data table UI for School, Class, Student management and Fee Type configuration forms on Admin Portal; integrate permissions to show/hide action buttons based on HQ / School roles. | Nito, Tyson | 7 | P2 - Medium | Done | UI complies with Design System; responsive layout; intuitive error/success feedback; client-side role rendering tests pass.
R8 | PB-06 | TSK-R8-01 | Documentation | Draft Technical Specification Docx for R8 (Singpass Auth & Parent Portal) | Write detailed .docx specification covering Singpass OIDC auth flow, Parent-Child Relationship Mapping architecture, PII security/encryption, API specs, and profile update rules. | Ryan, Nathan | 6 | P1 - High | Done | Complete .docx file with OIDC authentication flow and Authorize Access Token sequence; clearly defines editable vs read-only fields; approved by Security and Lead.
R8 | PB-07 | TSK-R8-02 | Database Refinement | Design Data Model & Migrations for Parents, Child Linkage, and Audit Log | Design data model and database schema for parent profiles, parent-child linkages, and profile change audit logs based on technical specification; apply indexing and encryption on sensitive personal data (PII). | Ryan, Nathan | 6 | P1 - High | Done | Migration script executes flawlessly; sensitive fields equipped with audit log schema; consistent foreign keys and constraints.
R8 | PB-06 | TSK-R8-03 | Backend / Auth | Integrate Singpass Authentication (Mock/Sandbox) & Parent-Student Authorization | Build service handling Singpass Auth callback, issuing Session JWT tokens; implement Parent Authorization middleware ensuring parents can access data only of legitimately linked students. | Ryan, Nathan | 8 | P1 - High | Done | Successful login via sandbox; IDOR vulnerability strictly prevented (no unauthorized access to other parents' children); comprehensive Unit & Integration Tests.
R8 | PB-08 | TSK-R8-04 | Backend / API | Build API for Account Details & Parent Profile Update | Build APIs for parents to view linked child Education Account balance and recent transactions, and update authorized personal contact details with change audit logs. | Ryan, Nathan | 7 | P1 - High | Done | API returns correct schema for balance/transaction history; profile update API validates standard Singapore formats; full old_value/new_value stored in audit log.
R8 | PB-15 | TSK-R8-05 | Frontend / UI | Build e-Service Portal UI: Account Dashboard & Profile Management | Develop UI on Parent e-Service Portal: Child selector screen, Education Account balance widget, transaction history table, and profile update on screen with client-side validation. | Ryan, Nathan | 8 | P1 - High | Done | Clean, responsive UI on multiple devices; handles Loading/Empty/Error states seamlessly; successful API integration.
R9 | PB-09 | TSK-R9-01 | Documentation | Draft Technical Specification Docx for R9 (Payment Engine & Outstanding Dues) | Write detailed .docx specification covering end-to-end payment flows: Dues lookup; Payment via Education Account (internal balance deduction); Online Payment Gateway (sandbox flow, webhook callbacks, idempotency key). | Lucas, Arthur | 4 | P1 - High | Done | Standardized .docx specification with Sequence Diagrams for both payment methods; payment error code table; network failure rollback scenarios; approved by BA and Lead.
R9 | PB-10 | TSK-R9-02 | Database Refinement | Design Data Model & Migrations for Transaction Management & Payment Gateway | Design data model and database schema for invoices, invoice line items, and payment transactions based on technical specification; add idempotency keys, transaction locking, and status audit logs. | Lucas, Arthur | 5 | P1 - High | Done | Migration script completed; verified ACID integrity constraints; locking mechanism prevents race conditions during concurrent payments; detailed Data Dictionary.
R9 | PB-10 | TSK-R9-03 | Backend Core | Build API for Outstanding Dues & Payment Logic using Education Account | API to retrieve outstanding fees by child; implement payment transaction via Education Account: check available balance, deduct balance, update dues status to PAID, and record ledger within a single database transaction. | Lucas, Arthur | 6 | P1 - High | Done | Transactions adhere to ACID and prevent race conditions (Pessimistic Locking); zero instances of balance deducted without invoice update; Unit Test coverage >= 90%.
R9 | PB-11 | TSK-R9-04 | Backend / Integration | Integrate Online Payment Gateway (Sandbox Gateway & Webhook) | Build service connecting online payment gateway (Sandbox API): initiate payment session, receive & verify webhook callbacks via HMAC signature, and auto-reconcile outstanding dues. | Lucas, Arthur | 6 | P1 - High | Done | Webhook verified with secure signature; webhook retry mechanism handled idempotently without duplicate charges; comprehensive reconciliation logs.
R9 | PB-09 | TSK-R9-05 | Frontend / UI | Build e-Service Portal UI: Outstanding Dues Lookup & Checkout Flow | Develop UI displaying outstanding charges, invoice selection, payment method selection (Education Account or Online Gateway), confirmation modal, and payment receipt view. | Lucas, Arthur | 5 | P1 - High | Done | Seamless checkout flow; submit button disabled against double clicks; clear error handling for insufficient funds; printable/downloadable PDF payment receipt.
R4 | PB-25 | TSK-R4-01 | AI/ML | Research document for rule-based | Research in MOE FAS system, identify characteristics in Singapore society including: avg income, minimum expense for living, health care,.. | Christian | 4 | P2-Medium | Done | Having a static rule-based inspired by society characters
R4 | PB-25 | TSK-R4-02 | AI/ML | Build demo static rule-based | Building python to test for score outcomes | Christian | 4 | P2-Medium | Done | Handle unexpected pre-defined secenarios such as fake old,
R4 | PB-25 | TSK-R4-03 | AI/ML | Synthetic data generate | Base-knowledge for simulate income data | Christian | 4 | P2-Medium | Done | Build in rules for synthetic data generation and having 100_000 samples

## Sprint Backlog 2
PBI Ref | Task ID | Category | Task Title | Description | Assignee | Estimate (Hours) | Priority | Status | Definition of Done (DoD) | Note
US-004 |  | Backend | Create CPF Service simulation | Simulate CPF service behaviour to later on can transfer money to this service as a real use case for later on integrated API | Kevin | 3h | Low | Done | Create only nessecary fields and simulation, not breaking the current system workflow.
|  | Backend | remaining Education Account funds transferred to CPF after closure | Transfer the remaing money in the education account to the CPF, set the balance to 0 | Kevin | 2h | Low | Done | No account with deactivate status should have money in the wallet
US-010 |  |  | view financial assistance information for my children |  | Lucas, Christian, Nathan, Ryan, Arthur |  |  | To do
US-018 |  | Backend | Desgin Create/Update Profile APIs, get Profile Detail API |  | Tyson |  | Low | Done |  | Personal Information thôi, không liên quan đến School
US-018 |  | Frontend | Design Profile Page, handle require update profile when login for the first time |  | Nito |  | Low | To do
US-026 |  | Backend | Prview and import academic-year, level and class CSV records | Implement bulk create classes for SU | Nito | 1h | Medium | In progress |  | Academic-years, Academic-levels, Class undone
US-026 |  | Frontend | Prview and import academic-year, level and class CSV records | Implement bulk create class page, export .xlxs template | Nito | 1h | Medium | In progress
US-027 |  | Backend | Import student records with optional class assignments and see per-row processing outcomes | Implement bulk create students for SU | Nito | 1h | Medium | To do
US-027 |  | Frontend | Import student records with optional class assignments and see per-row processing outcomes | Implment bulk create students page, export .xlxs template | Nito | 1h | Medium | To do
US-028 |  | Backend | Create API for search content for the eligible education accounts | All the education accounts must can be search by the MOE and the filter should point out exactly all the accounts with the suitable account | Kevin | 2h | High | Done | Search API returns eligible accounts accurately with filter and pagination support.
|  | Frontend | Implement frontend for education accounts list MOE User with search function | All the education accounts must be display within 1 page with pagination and filters function showed clearly with UI/UX | Kevin | 1h | Medium | Done | UI displays account list clearly with pagination, filters, and search functions.
|  | Backend | Create API Top-up for Education Account | Create a working API for top-up function for education accounts with the clean code and consistency in the codebase handling adding money to the education accounts | Hugh | 4h | High | Done | Top-up API successfully credits funds, updates balance, and logs errors properly.
|  | Backend | Create API to get transaction Top-up | Create a working API for transaction of the top-up for education accounts with the clean code and consistency in the codebase handling saving whenever there is a transactions | Hugh | 3h | Medium | Done | API retrieves top-up transactions with accurate filtering and details.
|  | Frontend | Add new UI for the top-up page | Create a seperated UI for top-up page with all the function within must be display clear with good UI/UX and the UI components should be consistent. | Kevin | 2h | High | Done | Top-up UI is fully integrated, validates inputs, and matches design specs.
|  | Frontend | Add table to view transaction Top-up history | Create a transaction top-up history table for MOE user to auditing all the transaction, helping the users can easily view and identified the transaction they made. | Kevin | 1h | Medium | Done | Transaction history table displays records clearly with sorting and pagination.
US-029 |  | Backend | Create API for the bulk top up campaigns configuration | Create an API to handle CRUD for the campaigns configuration, helping the MOE to later on can use these settings without setting up again | Hugh | 2h | High | Done | Bulk campaign configuration CRUD APIs are implemented and validated.
|  | Frontend | Implement frontend to config the bulk top up within the top up UI page | Display all the configurations were made by the MOE before with good UI/UX | Kevin | 1h | Medium | Done | Bulk config UI enables creating and managing campaign filters seamlessly.
US-030 |  | Backend | Preview selected acocunt and forecast top up on selected account | Create an API to handle showing education accounts with details after choosing the configuration or filtering the wanted criteria, as well as calculate the total top-up for each account. | Hugh | 2h | Medium | Done | Preview API returns accurate account list and forecasted top-up totals.
|  | Frontend | Implement selected preview modal to identified wrong criteria or spending if occurs | Create a UI modal to display the selected accounts after the configurations or the filter, help the MOE to overview what they chose to identify if there is any wrong information they need to change. | Kevin | 1h | Medium | Done | Preview modal displays selected accounts and total amount with confirmation flow.
US-031 |  | Backend | Create API for executing bulk top up within the configuration | Create an API for multiple top-up at once with multiple Nric requested within the configuration or the filter | Hugh | 2h | Medium | Done | Bulk top-up API processes multiple NRICs reliably with proper transaction records.
|  | Frontend | Implement frontend and handle bulking logic in UI | Implement clean UI for handle bulking function, can choose multiple account or the whole list after configuration settings or filtering the needed account. | Kevin | 3h | Medium | Done | Bulk execution UI handles multi-select and displays progress and outcome alerts.
US-032 |  | Backend | Create transaction history for individual and bulk | Create and handle audit logic so that the MOE user can check the consistency of the system after top-up for individuals as well as multiple education accounts | Hugh | 2h | Low | Done | Audit history API records and retrieves individual and bulk operations accurately.
|  | Frontend | Implement the transaction history table to audit the funding allocations and processing outcomes | Implement transaction history table with clean UI within the page so that the MOE user can check the consistency of the system after top-up for individuals as well as multiple education accounts | Kevin | 3h | Medium | Done | Audit table displays funding allocations and processing outcomes clearly.
US-034 |  | Backend | [API] Design Core CRUD Endpoints for Fee Types, Components, and Rate Rules | Design Core APIs: Establish the base REST API contracts and database schema for FeeTypes, FeeComponents, and FeeRateRules. Ensure standard CRUD operations are documented via Swagger/OpenAPI. | Tyson | 4H | Critical | Done
US-034 |  | Frontend | Design UI to working with fee-types, fee-components, fee-rate-rules |  | Nito |  | Critical | Done
US-035 |  | Backend | [Security] Implement Tenant Isolation and schoolId Authorization for Fee Configurations | Implement Multi-tenant RBAC APIs: Create robust authorization handlers to validate schoolId claims. Enforce strict tenant isolation on POST/PUT endpoints to ensure school users can only create or modify fee-types and fee-components within their authorized scope. | Tyson | 4H | High | Done
US-035 |  | Frontend | Implement UI base on user role to meet the requirement | School User can Create Fee-types and Fee-components for their own school by sending their schoolId in the API endpoint | Nito |  | Medium | Done
US-036 |  | Backend | [Command] Build Bulk Matrix Generation Logic for Fee Rate Rules | Implement Bulk Generation Command: Build a dedicated CQRS Command to accept the two matrix criteria as inputs and programmatically cross-join them to generate the specific fee-rate-rule combinations. Optimize the resulting bulk database inserts | Tyson | 4H | High | Done
US-036 |  | Frontend | Implement Fee Rate Rules Config Page for Fee Component | The Rate Rules should be in the matrix format, automatically map 2 criteria to generate each fee-rate-rule | Nito |  | Critical | Done
US-037 |  | Backend | [API] Create Initialization Endpoint for Fee Publications | Implement Fee Publication Creation Endpoint: Create an endpoint to accept publication metadata and the target scope criteria. Validate the payload and initialize the publication record in the database with a "Draft" or "Pending" state. | Tyson | 4H | High | Done
US-037 |  | Frontend | Implement Create Fee Publication Page | Users have to submit basic information and the scope for the batch | Nito |  | Critical | Done
US-038 |  | Backend | [Query] Implement Paginated Student Scope Evaluation Preview for Publications | Implement Publication Scope Preview Query: Build a read-only endpoint that dynamically evaluates the publication scope against the student database, returning a paginated preview of affected students and their estimated calculated charges before final execution. | Tyson | 4H | High | Done
US-038 |  | Frontend | Implement Fee Publication Result Preview Page | Planning | Nito |  | Low | Done
US-039 |  | Backend | [Background Job] Build Async Processor and SignalR Hub for Fee Publishing Status | Build the publish endpoint to immediately update the database status to "PROCESSING". Offload the heavy charge calculation and distribution logic to a background processor (e.g., Hangfire or an event-driven worker) and configure a SignalR hub to stream progress tracking percentages back to the client. | Tyson | 4H | Critical | Done
US-039 |  | Frontend | Implement Publish Button for Fee Publications | When click the publish button, the status of batch instantly change to "PROCESSING". Planning on implement realtime loading UI to check the progress | Nito |  | Critical | Done
US-040 |  | Backend | [Integration] Develop Student Charge Detail API and Sync with Billing Service | Implement Charge Detail & Billing Sync: Create an API to aggregate and serve detailed student charge breakdowns. Implement an integration layer to securely communicate with the internal billing microservice (via HTTP client or message bus) to fetch and sync real-time payment statuses. | Tyson | 4H | Critical | Done
US-40 |  | Frontend | Implement Student Charge Detail Page | The Detail Page should show the real amount of money charged. Planning on integrate with the billing service to check the paying status | Nito |  | High | To do
US-041 |  | Backend | Implement FAS Application Submission API in E-Service | As a Parent, I want to submit an FAS Application for a verified EA-linked child using household and income information, so that the child can be assessed for eligible financial assistance. | Christian |  |  | In progress |  | Source Ref: R10
US-041 |  | Frontend | Implement FAS Application Submission Form UI in E-service | As a Parent, I want to submit an FAS Application for a verified EA-linked child using household and income information, so that the child can be assessed for eligible financial assistance. | Arthur |  | Medium | In progress | Integrated APIs and work normally via UI
US-042 |  | Backend | Implement backend service for School-Submitted FAS Applications | As a School User, I want to submit FAS Applications received on paper for any student at my school including those without an EA, so that offline applicants enter the same assessment process. | Christian |  |  | In progress |  | Source Ref: R5
US-042 |  | Frontend | Implement UI for School-Submitted FAS Application Form | As a School User, I want to submit FAS Applications received on paper for any student at my school including those without an EA, so that offline applicants enter the same assessment process. | Arthur |  | Low | To do | Integrated APIs and work normally via UI
US-043 |  | AI/ML | Implement AI-Based OCR to Prefill FAS Application Fields | As a School User, I want uploaded paper-form images to prefill selected application fields for my review, so that manual entry is faster without granting authority to unverified OCR values. | Christian |  |  | To do |  | Source Ref: R5
US-044 |  | Database | Design schemas for MOE FAS management | Design all required tables and fields needed to create/update and retrieve MOE FAS scheme records | Ryan | 6h | Critical | Done | Migration scripts executes successfully on target SQL Server instance; all tables, constraints, indexes, and sequences are created without errors.
|  | Backend | Init entities/schemas for MOE FAS | Create entities, sql script for db project and seed data script (if needed) for MOE FAS scheme | Ryan | 4h | Critical | Done | Base entity mapped cleanly to all MOE FAS entities
|  | Frontend | Create mock UI for MOE FAS screen | Create components, state handling for MOE FAS scheme list screen | Nathan | 5h | Medium | Done | UI components and state management for MOE FAS screen are implemented with mock data, matching wireframe specifications.
|  | Backend | Create Get MOE Scheme Details endpoint | Develop the API to fetch scheme details by ID: Retrieve data from moe_fas_schemes, nationalities, configured subsidies and budget details | Ryan | 4h | Medium | Done | API retrieves full scheme details by ID including scheme info, eligible nationalities, subsidies, and budget summary.
|  | Backend | Create Get All Active Schemes endpoint | Develop the API to retrieve all active schemes: Enforce the query filter WHERE is_deleted = false. Support pagination, sort, and provide basic filtering by status. Return core scheme details with budget summary. | Ryan | 4h | Medium | Done | API returns active schemes (WHERE is_deleted = false) with functional pagination, sorting, and status filtering.
|  | Frontend | UI: Schemes List Page (Get All & Suspend Integration) | Build a Data Table displaying schemes from moe schemes. Add a modal action triggering suspend with a confirmation dialog. | Nathan | 5h | Medium | Done | Data table correctly renders MOE schemes from API; suspend modal action triggers confirmation dialog and successfully calls suspend endpoint.
|  | Frontend | UI: Scheme Details Modal (Get by ID Integration) | Build a detailed view for a scheme by id: Display header overview, current status, Eligible Nationalities card, and Subsidies grid/tabs categorized by Primary, Secondary, and Pre-University. | Nathan | 4h | Medium | Done | Detailed modal displays complete scheme overview, status, eligible nationalities, and subsidy grids categorized by education stage.
US-045 |  | Frontend | Implement UI pages for school user to configure SBFAS | As a School User, I want to configure and activate school-owned SBFAS Schemes with free-text eligibility descriptions, so that my school can offer tiered assistance subject to manual review. | Arthur |  | Critical | In progress | Integrated APIs and work normally via UI | Source Ref: R6
|  | Backend | Implement BE for school user to configure SBFAS flow | As a School User, I want to configure and activate school-owned SBFAS Schemes with free-text eligibility descriptions, so that my school can offer tiered assistance subject to manual review. | Lucas |  | Critical | In progress |  | Source Ref: R7
US-046 |  | Backend | Create Suspend Scheme endpoint | Develop the API to transition a scheme's status to SUSPEND. Validate allowed source states (e.g., from OPEN_APPLICATION or DRAFT). Update status = 'SUSPEND' and write an audit log entry recording the timestamp and operator. | Ryan | 4h | Medium | Done | API validates current state, transitions scheme status to SUSPEND, and creates audit log entry with timestamp and operator.
|  | Backend | Create insert MOE FAS scheme endpoint for MOE user | Develop the API to add a new MOE scheme with all related information: general, eligibility criterias and subsidies for fee components of different academic level | Ryan | 5h | Medium | Done | API successfully creates new MOE FAS scheme with general info, eligibility criteria, and academic level subsidies.
|  | Frontend | UI: Add button to Suspend Scheme that has APPLICATION_OPEN status, apply rule check before submitting to server | Build a flow to check scheme status before sending suspend status request to the server | Nathan | 3h | Medium | Done | Suspend button displays only for schemes with APPLICATION_OPEN status; checks status rule before sending suspend request to server.
|  | Frontend | UI: Scheme Creation Form (Create Scheme Integration) | Build a flow integrated with all necessary components to complete the add MOE schemes flow (name, eff_from, eff_to,...) | Nathan | 5h | Medium | Done | Scheme creation form integrates all required fields (name, effective dates, eligibility criteria), validates inputs, and submits to backend successfully.
US-047 |  | Backend | Create Add Fee Component endpoint | Develop the API to configure/add subsidy fee components: Accept education_stage, fee_component_id, and subsidy_percentage. Enforce the business rule: Only allowed when scheme status is DRAFT or SUSPEND. Validate 0 < subsidy_percentage <= 100 and check for duplicate | Ryan | 5h | Medium | Done | API adds subsidy fee component with valid percentage (0 < % <= 100), enforces DRAFT/SUSPEND scheme status, and prevents duplicates.
|  | Frontend | Service Integration: API Client for 5 Endpoints | Define interfaces/types matching the schema (MoeScheme, Nationality, Subsidy, Budget, SchemeStatus). Implement an API service wrapper covering all 5 endpoints | Nathan | 5h | Medium | In progress | API client service interfaces and typed wrappers for all 5 MOE FAS endpoints are implemented and fully unit-tested.
|  | Frontend | UI: Add Fee Component Modal (Add Fee Component Integration) | Build an "Add Fee Component" modal: Select Education Stage, select fee_component_id (dropdown), and enter subsidy_percentage . Disable button/action if scheme is not in DRAFT, PUBLISHED or SUSPEND (with tooltip explaining suspension is required first). | Nathan | 4h | Medium | Done | Modal properly captures education stage, fee component, and subsidy percentage with validation (0 < % <= 100), enforcing status rules with tooltips.
|  | Backend | Add fee component subsidy addition endpoint for MOE scheme | Complete API, finish business rule check before allow to add fee subsidy for existing MOE FAS schemes | Ryan | 3h | Medium | Done | API validates business rules and active scheme context before saving fee component subsidy configuration cleanly.
|  | Frontend | Add fee component subsidy screen for MOE FAS scheme | Add components, MOE FAS fee component subsidy screen and apply frontend validation rule check before submitting the payloat to backend | Nathan | 4h | Medium | In progress | Fee component subsidy UI screen handles user input, applies frontend validation rules, and dispatches payload to backend properly.
|  | Frontend | Implement UI pages for school user to configure percentage or fixed subsidies by Education Stage and Fee Component | As an authorized School User, I want to configure percentage or fixed subsidies by Education Stage and Fee Component, so that supported charges receive the correct capped subsidy without affecting unsupported fees. | Arthur |  | Medium | To do
|  | Backend | Implement BE services and databases for school user to configure percentage or fixed subsidies by Education Stage and Fee Component | As an authorized School User, I want to configure percentage or fixed subsidies by Education Stage and Fee Component, so that supported charges receive the correct capped subsidy without affecting unsupported fees. | Lucas |  | Medium | In progress
US-048 |  | Backend | Implement Scheme Assessment Round Budget and Deadline Management | As an authorized FAS administrator, I want to establish the available budget and application deadline for scheme assessment rounds, so that grants do not commit funds beyond approved limits. | Christian |  |  | To do
US-049 |  | Backend | Add logic to automatically assess applications match eligibility criterias | Add a function to handle application assessment to reject/accept it, and integrate that function to the application submission flow | Ryan | 5h | Medium | In progress | Assessment logic accurately and automatically evaluates applicant criteria against eligibility rules and budget limits to auto approve or reject.
US-050 |  | Frontend | Implement UI for School-Based Scheme Application Review | As a School User, I want to review applications not granted through MOEFAS and Grant or Reject a school-based scheme, so that school assistance decisions remain under authorized human control. | Arthur |  | Low | To do | Integrated APIs and work normally via UI
US-050 |  | Backend | Implement backend service for School-Based Scheme Application Review | As a School User, I want to review applications not granted through MOEFAS and Grant or Reject a school-based scheme, so that school assistance decisions remain under authorized human control. | Lucas |  |  | To do
US-051 |  | Backend | Implement Subsidy Calculation and Application for Unpaid Charges | As an authorized FAS administrator, I want approved subsidies calculated and applied to supported unpaid charges before their due dates, so that parents pay the correct nonnegative Net Payable while Original Amount stays unchanged. | Christian |  |  | In progress
US-052 |  | AI/ML | Implement AI-Powered SBFAS Scheme Recommendations | As a School User, I want optional AI recommendations of applicable SBFAS schemes, so that I can review applications more efficiently while keeping the grant decision under my control. | Christian |  |  | To do
US-053 |  | Backend | Add status column in database and add params filter and sort | As a parent, I want to filter the outstanding fees by their status; when choose Both option, I want to input my desired amount of EA balance to pay | Lucas |  | Medium | Done |  | These are r9
US-053 |  | Frontend | Add status column in UI table and filter dropdown | As a parent, I want to filter the outstanding fees by their status; when choose Both option, I want to input my desired amount of EA balance to pay | Arthur |  | Medium | Done | Integrated APIs and work normally via UI

## Overview Sprint Backlog 2
PBI Ref | Task ID | Category | Task Title | Description | Assignee | Estimate (Hours) | Priority | Status | Definition of Done (DoD)
US-004 |  |  |  |  | Kevin,Hugh |  |  | To do
US-010 |  |  |  |  | Lucas, Christian, Nathan, Ryan, Arthur |  |  | To do
US-018 |  |  |  | Personal Information thôi, không liên quan đến School | Nito, Tyson |  |  | To do
US-026 |  |  |  | Academic-years, Academic-levels, Class undone | Nito, Tyson |  |  | To do
US-027 |  |  |  |  | Nito, Tyson |  |  | To do
US-028 |  |  |  |  | Kevin,Hugh |  |  | To do
US-029 |  |  |  |  | Kevin,Hugh |  |  | To do
US-030 |  |  |  |  | Kevin,Hugh |  |  | To do
US-031 |  |  |  |  | Kevin,Hugh |  |  | To do
US-032 |  |  |  |  | Kevin,Hugh |  |  | To do
US-034 |  |  |  |  | Nito, Tyson |  |  | To do
US-035 |  |  |  |  | Nito, Tyson |  |  | To do
US-036 |  |  |  |  | Nito, Tyson |  |  | To do
US-037 |  |  |  |  | Nito, Tyson |  |  | To do
US-038 |  |  |  |  | Nito, Tyson |  |  | To do
US-039 |  |  |  |  | Nito, Tyson |  |  | To do
US-040 |  |  |  |  | Nito, Tyson |  |  | To do
US-041 |  |  |  | Source Ref: R10 | Lucas, Christian, Nathan, Ryan, Arthur |  |  | To do
US-042 |  |  |  | Source Ref: R5 | Lucas, Christian, Nathan, Ryan, Arthur |  |  | To do
US-043 |  |  |  | Source Ref: R5 | Lucas, Christian, Nathan, Ryan, Arthur |  |  | To do
US-044 |  |  |  |  | Lucas, Christian, Nathan, Ryan, Arthur |  |  | To do
US-045 |  |  |  | Source Ref: R6 | Lucas, Christian, Nathan, Ryan, Arthur |  |  | To do
US-046 |  |  |  |  | Lucas, Christian, Nathan, Ryan, Arthur |  |  | To do
US-047 |  |  |  |  | Lucas, Christian, Nathan, Ryan, Arthur |  |  | To do
US-048 |  |  |  |  | Lucas, Christian, Nathan, Ryan, Arthur |  |  | To do
US-049 |  |  |  |  | Lucas, Christian, Nathan, Ryan, Arthur |  |  | To do
US-050 |  |  |  |  | Lucas, Christian, Nathan, Ryan, Arthur |  |  | To do
US-051 |  |  |  |  | Lucas, Christian, Nathan, Ryan, Arthur |  |  | To do
US-052 |  |  |  |  | Lucas, Christian, Nathan, Ryan, Arthur |  |  | To do

## Kanban Board Sprint 1
SPRINT PROGRESS KANBAN BOARD
TOTAL TASKS |  | TO DO |  | IN PROGRESS |  | DONE |  | COMPLETION RATE |  | TOTAL HOURS
22 |  | 0 |  | 0 |  | 22 |  | 100% |  | 130
100% of sprint scope |  | 0,0% of total |  | 0,0% of total |  | 100,0% of total |  | Target: 100% |  | Estimated hours (h)
TO DO (0) |  |  |  | IN PROGRESS (0) |  |  |  | DONE (22)
Task ID | Task Title | Assignee | Estimate (h) | Task ID | Task Title | Assignee | Estimate (h) | Task ID | Task Title | Assignee | Estimate (h)
[8 empty] | TSK-R1-01 | Draft Technical Specification Docx for R1 (Education Account Lifecycle) | Kevin,Hugh | 4
[8 empty] | TSK-R1-02 | Design Data Model & Migrations for Education Account Lifecycle | Hugh | 5
[8 empty] | TSK-R1-03 | Build Scheduled Job to automatically create & activate accounts at age 7 | Kevin | 4
[8 empty] | TSK-R1-04 | Build Scheduled Job to automatically close accounts & transfer settlement to CPF at age 16 | Kevin | 4
[8 empty] | TSK-R1-05 | Build Wallet CRUD APIs (create, credit, debit, update status, and get wallet) & Wallet Transaction functionality to handle wallet behavior, including APIs to retrieve and reverse transactions. | Hugh | 8
[8 empty] | TSK-R3-01 | Draft Technical Specification Docx for R3 (Master Data & Fee Management) | Nito, Tyson | 6
[8 empty] | TSK-R3-02 | Design Data Model & Migrations for School Master Data & Fee Catalog | Nito, Tyson | 7
[8 empty] | TSK-R3-03 | Build Master Data CRUD APIs (School, Level, Class, Student) and RBAC Guard | Nito, Tyson | 8
[8 empty] | TSK-R3-04 | Build Fee Type Configuration Module & Student Charge Generation | Nito, Tyson | 8
[8 empty] | TSK-R3-05 | Build School Management & Fee Configuration UI (Admin Portal) | Nito, Tyson | 7
[8 empty] | TSK-R8-01 | Draft Technical Specification Docx for R8 (Singpass Auth & Parent Portal) | Ryan, Nathan | 6
[8 empty] | TSK-R8-02 | Design Data Model & Migrations for Parents, Child Linkage, and Audit Log | Ryan, Nathan | 6
[8 empty] | TSK-R8-03 | Integrate Singpass Authentication (Mock/Sandbox) & Parent-Student Authorization | Ryan, Nathan | 8
[8 empty] | TSK-R8-04 | Build API for Account Details & Parent Profile Update | Ryan, Nathan | 7
[8 empty] | TSK-R8-05 | Build e-Service Portal UI: Account Dashboard & Profile Management | Ryan, Nathan | 8
[8 empty] | TSK-R9-01 | Draft Technical Specification Docx for R9 (Payment Engine & Outstanding Dues) | Lucas, Arthur | 4
[8 empty] | TSK-R9-02 | Design Data Model & Migrations for Transaction Management & Payment Gateway | Lucas, Arthur | 5
[8 empty] | TSK-R9-03 | Build API for Outstanding Dues & Payment Logic using Education Account | Lucas, Arthur | 6
[8 empty] | TSK-R9-04 | Integrate Online Payment Gateway (Sandbox Gateway & Webhook) | Lucas, Arthur | 6
[8 empty] | TSK-R9-05 | Build e-Service Portal UI: Outstanding Dues Lookup & Checkout Flow | Lucas, Arthur | 5
[8 empty] | TSK-R4-01 | Research document for rule-based | Christian | 4
[8 empty] | TSK-R4-02 | Build demo static rule-based | Christian | 4